## Slide 1: NC Rejuvenation Programme - Project Kickoff
Rimba Heights NC & Cendana Central NC | 10 Feb 2026

## Slide 2: Why rejuvenate?
• Footfall at both NCs down about 15% since 2022
• Ageing shopfronts and poor lighting (feedback cases)
• Trade mix skewed: 3 hair salons, no pharmacy at Rimba Heights NC
• Vacancy above town average

## Slide 3: Objectives
• Refresh common areas with the Town Council
• Rebalance trade mix at renewals and tenders
• Pilot wider display areas to animate walkways
• Lift occupancy to 98% by end 2027

## Slide 4: Scope
Workstream | Lead | Partner
Physical upgrading | Benjamin Ho | Kebun Raya-Rimba TC
Trade mix & leasing | Nurul Huda Rahman | -
Policy (display pilot) | Rajesh Pillai | -
Tenant engagement | Grace Chua | Merchants' association
Data & tracking | Kelvin Goh | -

## Slide 5: Timeline
Phase | Period
Design & consultation | Mar - Jun 2026
Display pilot | Aug 2026 - Jul 2027
Upgrading works | Jan - Sep 2027
Review | Oct 2027

## Slide 6: Trade mix approach
• Hold essential trades at every NC (POL-001 cl. 4)
• Use the concentration limit of 2 per trade at renewals
• Target trades: pharmacy, eldercare, enrichment
• Use precedents for change-of-trade decisions

## Slide 7: Stakeholders
• Tenants and merchants' association
• Town Councils
• Residents' committees
• Members of Parliament (feedback channel)

## Slide 8: Risks
• Tenant disruption during works: provide rent rebate guidelines
• Budget overrun
• Resistance to trade mix changes

## Slide 9: KPIs
KPI | Baseline | Target
Occupancy | 95.8% | 98%
Feedback cases / month | 14 | < 8
Footfall index | 85 | 100

## Slide 10: Next steps
• Form working committee (Feb)
• Tenant briefing sessions (Mar)
• Draft display-area circular (by Jul)